NCDA COMMITTEE MIDYEAR REPORT

PUBLICATION DEVELOPMENT COUNCIL (PDC)

March 15, 2025

Leadership Information

Current PDC Chair: Open

List Committee Members (no contact information required)

| PDC Member | Role | Term | Term end date |
| --- | --- | --- | --- |
| Heather Robertson | Member | 1 | 2024 |
| Jessamyn Perlus | Member | 1 | 2025 |
| Spencer (Skip) Niles | Member | 1 | 2025 |
| Darrin Carr | CG7 Coordinator |  |  |
| Melanie Reinersman | NCDA Staff |  |  |
| Julia Makela | Board Liaison |  |  |

Committee Activities to Date

- The PDC met virtually in Nov. 2024

- PDC discussion with Board (Oct 2024) and new Task Force approved (Dec 2024); six members selected and began meeting; new activities of the PDC put on hold (including consideration of publications or potential members) until Task Force submits report (slated for August 2025)

- One new content review for CG7 completed then published (meets Strategic Goal for Career Empowerment: publications)

- NACADA contract signed by Board for a joint publication on career advising; editorial team selected and kick-off meeting held (meets Strategic Goal for Community: collaborations)

- Second option open for reading a monograph in The Hub for CEs (ethics; Makela & Perlus, 2017) (meets Strategic Goal for Career Empowerment: professional development)

- New monograph on mental health (planned for 2025, Curry & Manton, eds) call for chapter authors sent (meets Strategic Goal for Career Empowerment: diversity of authors)

- Monitored the new NCDA epublisher, VitalSource, for 3 books: CG7, Cultural Competence and  Holland; 8 sold (meets Strategic Goal for Career Empowerment: publications)

Projected Plan/Work to be completed through September 30

- Continue Task Force work, clarifying the scope and future direction of the PDC

- Continue CG7 content review and publish a new review each quarter

- Implement CE credits in the Hub for reading Strengths monograph

- Schedule a zoom call with mental health monograph team

- Continue to monitor sales with new epublisher

- Hold a PDC meeting at the Conference, including the Task Force